## checklist
Sr. No. | Requirements | For Compairing Context Source | Suggestions after compairing both RFP+Company Documents | Criticality | Evaluation | Score
1 | Full solicitation received (RFP, RFQ, drawings, specs, addenda) in the bid document? | RFP-only |  | C | YES - 0
2 | U.S. federal/state/local procurement requirements reviewed? | RFP-only |  | C | YES - 0
3 | All bid instructions, deadlines, and addenda understood? | RFP-only |  | C | YES - 0
4 | Any ambiguities or missing info required? Clarification with the contracting officer/owner required? | RFP-only |  | C | YES - 0
5 | What is the project state and is company registered and licensed for work in the project state? | RFP+Company |  | C | YES - 2, PARTIAL -1, NO -0
6 | What are the minimum qualifications? Do company meet all mandatory minimum qualifications (experience, capabilities, safety record, etc.) as per the project? | RFP+Company |  | C | YES - 2, PARTIAL -1, NO -0
7 | Is any SBE, WBE, MBE requirement in project? Can company meet Diversity/Small Business goals (e.g., SBE, WBE, MBE) if mandatory? | RFP+Company |  | C | YES - 2, PARTIAL -1, NO -0
8 | Is any security clearence is required? Are these obtainable for the company? | RFP+Company |  | C | NO - 2, PARTIAL - 1, YES - 0
9 | Is any Environmental/Permitting risks (NEPA, state laws) are required? Are these understood and manageable by the company? | RFP+Company |  | C | YES - 2, PARTIAL -1, NO -0
10 | Is Project scope clear and achievable with our company's capabilities? | RFP+Company |  | C | YES - 2, PARTIAL -1, NO -0
11 | Is any Labor relations/Union requirements? If so, are these requirements understood and manageable? | RFP+Company |  | C | NO - 2, PARTIAL - 1, YES - 0
12 | Is sufficient data (geotech, survey) are available in bid document? | RFP-only |  | C | YES - 2, PARTIAL -1, NO -0
13 | Is Site investigation conducted or required? | RFP+Company |  | C | NO - 2, PARTIAL - 1, YES - 0
14 | What are Major technical, commercial, and execution risks required in the bid? Are they identified and manageable by the company? | RFP+Company |  | C | YES - 2, PARTIAL -1, NO -0
15 | Adequate time and internal resources are available for quality proposal preparation by the company? | RFP+Company |  | C | YES - 2, PARTIAL -1, NO -0
16 | Internal team and key partners (especially engineering) are available? | RFP+Company |  | C | YES - 2, PARTIAL -1, NO -0
17 | Critical vendors, equipment, and subcontractors are available and can comply with project terms? | RFP+Company |  | C | YES - 2, PARTIAL -1, NO -0
18 | Is any adherence to 'BABA/BAA' or other domestic content rules is required in the BID ? | RFP+Company |  | C | NO - 2, PARTIAL - 1, YES - 0
19 | Is it possible for the company to fulfil the BABA/BAA complaince ? | RFP+Company |  | C | YES - 2, PARTIAL -1, NO -0
20 | Is any Contractual Terms & Conditions (indemnity, liability, payment) are required in the BID? | RFP+Company |  | C | NO - 2, PARTIAL - 1, YES - 0
21 | Are these terms and conditions acceptable by the company? | RFP+Company |  | C | YES - 2, PARTIAL -1, NO -0
22 | Is any Required bonds (bid, performance, payment) and insurances in the BID can be secured by the company? | RFP+Company |  | C | YES - 2, PARTIAL -1, NO -0
23 | Is Project aligning with our company's current strategic goals and risk profile? | RFP+Company |  | C | YES - 2, PARTIAL -1, NO -0